## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After Day… | [13 empty] | Measured in hours
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
All - supporting Corey | Account Creation and Login ASP | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
All - supporting Corey | Account Creation and login Web | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
All - supporting Saul | Account Creation and login Desktop | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
All - supporting Corey | Create DB | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create Source Corey | Create Pdf link source web and asp | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 6 | 2 | 0
Create Source Saul | Create Pdf link source Desktop | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Create Note Corey | create note for source web and asp | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
Create Note Saul | create note for source desktop | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Estimate Totals | 30 | 29.5 | 24 | 24 | 24 | 24 | 20 | 20 | 18 | 18 | 18 | 18 | 22 | 18 | 12